## Instructions
Project Plan Template – Instructions
Purpose
What is this? | A structured project plan template for tracking phases, tasks, milestones, owners, dates, and progress in one place.
Who is it for? | Project managers, PMO leads, and team leads managing projects of any size.
How to use | Fill in the Project Overview tab first, then populate the Project Plan tab with your WBS.
Sheets Overview
Instructions | This sheet – guidance on using the template.
Project Overview | High-level project charter: objectives, scope, stakeholders, key dates.
Project Plan | Full work breakdown structure (WBS) with tasks, dates, owners, and status.
Project Plan – Column Guide
ID | WBS number (e.g. 1, 1.1, 1.1.1). Use hierarchy to group phases and tasks.
Type | Phase / Milestone / Task. Phases are top-level groupings; Milestones are key checkpoints.
Phase | The phase this task belongs to (e.g. Initiation, Planning, Execution).
Task / Deliverable | Description of the work item or deliverable.
Owner | Person responsible for delivering this item.
Start Date | Planned start date. Format: DD/MM/YYYY.
End Date | Planned end date. Format: DD/MM/YYYY.
Duration (days) | Auto-calculated: End Date – Start Date + 1.
% Complete | Enter as a whole number (e.g. 75 for 75%). Auto-formats as percentage.
Status | Pick from dropdown: Not Started / In Progress / On Hold / Completed / Cancelled.
Priority | Pick from dropdown: Low / Medium / High / Critical.
Dependencies | ID(s) of predecessor tasks (e.g. 1.2, 2.1).
Notes | Any additional context, risks, or comments.
Status Colour Legend
Not Started | Use this status for items that are not yet begun.
In Progress | Use this status for items that are currently being worked on.
On Hold | Use this status for items that are paused or blocked.
Completed | Use this status for items that are fully done.
Cancelled | Use this status for items that are no longer required.
Best Practices
Keep IDs consistent | Use a clear WBS numbering scheme (1, 1.1, 1.1.1) from the start and don't change it mid-project.
Update weekly | Review status and % Complete every week during your project status meeting.
Use Milestones | Mark key decision points and deliverable handoffs as Milestones so they stand out.
Log dependencies | Fill in the Dependencies column – it helps spot bottlenecks before they happen.
Archive completed | At project close, save a copy of this file as your project archive record.
PMO Mastery ¦ Project Plan Template ¦ pmomastery.com

## Project Overview
Project Overview
Project Information
Project Name |  | Project Code
Project Manager |  | Sponsor
Department / Division |  | Programme
Start Date |  | Target End Date
Actual End Date |  | Budget (€)
Project Phase |  | Priority
Objectives & Scope
Project Objectives
In Scope
Out of Scope
Key Assumptions
Key Constraints
Stakeholders
Name | Role / Title | Interest | Influence
Jan de Vries | Project Sponsor | High | High
Sophie Bakker | Project Manager | High | High
Ahmed Al-Rashid | IT Lead | Medium | Medium
Maria Gonzalez | Business Analyst | High | Low
Thomas Müller | Steering Committee | Low | High
Key Milestones
Milestone | Target Date | Actual Date | Status
Project Kick-off |  |  | Not Started
Requirements Approved |  |  | Not Started
Design Sign-off |  |  | Not Started
Pilot / UAT Complete |  |  | Not Started
Go-Live |  |  | Not Started
Project Closure |  |  | Not Started
PMO Mastery ¦ Project Plan Template ¦ pmomastery.com

## Project Plan
Project Plan
ID | Type | Phase | Task / Deliverable | Owner | Start Date | End Date | Duration (days) | % Complete | Status | Priority | Dependencies | Notes
1 | Phase | Initiation | Initiation Phase |  | 2026-05-01 | 2026-05-15 | 15 | 80% | In Progress | High
1.1 | Milestone | Initiation | Project Kick-off | Sophie Bakker | 2026-05-01 | 2026-05-01 | 1 | 100% | Completed | High |  | Kick-off meeting completed with all stakeholders
1.2 | Task | Initiation | Define project charter | Sophie Bakker | 2026-05-02 | 2026-05-06 | 5 | 100% | Completed | High |  | Approved by sponsor
1.3 | Task | Initiation | Identify stakeholders | Jan de Vries | 2026-05-05 | 2026-05-09 | 5 | 50% | In Progress | Medium | 1.2
1.4 | Task | Initiation | Agree governance structure | Sophie Bakker | 2026-05-10 | 2026-05-15 | 6 | 0% | Not Started | Medium | 1.3
2 | Phase | Planning | Planning Phase |  | 2026-05-18 | 2026-06-12 | 26 | 0% | Not Started | High | 1
2.1 | Task | Planning | Develop project plan | Sophie Bakker | 2026-05-18 | 2026-05-29 | 12 | 0% | Not Started | High | 1.4
2.2 | Task | Planning | Resource planning & allocation | Jan de Vries | 2026-05-18 | 2026-05-22 | 5 | 0% | Not Started | Medium | 1.4
2.3 | Task | Planning | Risk & issue register setup | Ahmed Al-Rashid | 2026-05-25 | 2026-05-29 | 5 | 0% | Not Started | Medium | 2.1 | Use RAID Log Template
2.4 | Task | Planning | Requirements gathering & sign-off | Maria Gonzalez | 2026-05-25 | 2026-06-05 | 12 | 0% | Not Started | High | 2.1
2.5 | Milestone | Planning | Requirements Approved | Sophie Bakker | 2026-06-12 | 2026-06-12 | 1 | 0% | Not Started | High | 2.4
3 | Phase | Execution | Execution Phase |  | 2026-06-15 | 2026-08-21 | 68 | 0% | Not Started | High | 2
3.1 | Task | Execution | Solution design & architecture | Ahmed Al-Rashid | 2026-06-15 | 2026-06-26 | 12 | 0% | Not Started | High | 2.5
3.2 | Milestone | Execution | Design Sign-off | Jan de Vries | 2026-06-30 | 2026-06-30 | 1 | 0% | Not Started | High | 3.1
3.3 | Task | Execution | Development / implementation | Ahmed Al-Rashid | 2026-07-01 | 2026-07-31 | 31 | 0% | Not Started | High | 3.2
3.4 | Task | Execution | Testing (unit & integration) | Thomas Müller | 2026-08-01 | 2026-08-14 | 14 | 0% | Not Started | High | 3.3
3.5 | Task | Execution | User Acceptance Testing (UAT) | Maria Gonzalez | 2026-08-10 | 2026-08-21 | 12 | 0% | Not Started | High | 3.4
3.6 | Milestone | Execution | Pilot / UAT Complete | Sophie Bakker | 2026-08-21 | 2026-08-21 | 1 | 0% | Not Started | High | 3.5
4 | Phase | Go-Live | Go-Live & Transition |  | 2026-08-24 | 2026-09-04 | 12 | 0% | Not Started | Critical | 3
4.1 | Task | Go-Live | Go-live preparation & cutover plan | Ahmed Al-Rashid | 2026-08-24 | 2026-08-28 | 5 | 0% | Not Started | Critical | 3.6
4.2 | Milestone | Go-Live | Go-Live | Sophie Bakker | 2026-09-01 | 2026-09-01 | 1 | 0% | Not Started | Critical | 4.1
4.3 | Task | Go-Live | Hypercare & stabilisation | Thomas Müller | 2026-09-02 | 2026-09-04 | 3 | 0% | Not Started | High | 4.2
5 | Phase | Closure | Project Closure |  | 2026-09-07 | 2026-09-18 | 12 | 0% | Not Started | Medium | 4
5.1 | Task | Closure | Lessons learned session | Sophie Bakker | 2026-09-07 | 2026-09-11 | 5 | 0% | Not Started | Medium | 4.3
5.2 | Task | Closure | Final reporting & documentation | Maria Gonzalez | 2026-09-07 | 2026-09-14 | 8 | 0% | Not Started | Medium | 4.3
5.3 | Milestone | Closure | Project Closure | Jan de Vries | 2026-09-18 | 2026-09-18 | 1 | 0% | Not Started | Medium | 5.1 | Formal sign-off by sponsor
PMO Mastery ¦ Project Plan Template ¦ pmomastery.com