## Instructions
RAID Log – Instructions
Purpose
What is a RAID Log? | A RAID Log tracks Risks, Assumptions, Issues, and Dependencies in a single place, giving the project team a structured view of items that could affect delivery.
Who owns it? | The Project or PMO Manager owns the RAID Log. Each item has an individual Owner responsible for updates and actions.
How often to update? | Review weekly during project meetings. Update statuses, scores, and action progress after each review.
Sheet Guide
Risks | Items that could negatively affect the project if they occur. Scored by Probability × Impact.
Assumptions | Conditions assumed to be true. Must be validated; if wrong, they become risks or issues.
Issues | Problems that have already occurred and require active resolution.
Dependencies | Internal or external items the project relies on. Track status and impact if delayed.
Risk Scoring Matrix (Probability × Impact)
| Low Impact (1) | Medium Impact (2) | High Impact (3)
Low Prob (1) | 1 – Low | 2 – Low | 3 – Medium
Medium Prob (2) | 2 – Low | 4 – Medium | 6 – High
High Prob (3) | 3 – Medium | 6 – High | 9 – Critical
Best Practices
Raise early | Log risks and assumptions at project kick-off. Early visibility allows timely action.
Be specific | Write clear, unambiguous descriptions. Vague entries are hard to act on.
Assign owners | Every item must have a named owner accountable for monitoring and resolution.
Review regularly | RAID items go stale quickly. Make it a standing agenda item in your project meetings.
Close items | Mark items Closed/Resolved when done. Keep the log focused on active items.
PMO Mastery ¦ RAID Log ¦ pmomastery.com

## Risks
RAID Log – Risks
Risk ID | Risk Description | Category | Risk Owner | Probability (1-3) | Impact (1-3) | Risk Score (P×I) | Response Strategy | Mitigation Actions | Contingency Plan | Status | Date Raised | Review Date | Notes
R-001 | Key vendor unable to deliver software licences on time | External | Jan de Vries | 2 | 3 | 6 | Reduce | Identify and qualify alternative vendor by end of May | Procure licences from backup vendor at 15% premium | Open | 2026-04-01 | 2026-05-01 | Vendor under financial review
R-002 | Insufficient senior stakeholder engagement leads to scope creep | Strategic | Sophie Müller | 3 | 3 | 9 | Avoid | Schedule monthly steering committee; circulate scope baseline | Escalate to sponsor for scope re-baselining decision | In Progress | 2026-04-05 | 2026-04-30 | First SteerCo scheduled 29 Apr
R-003 | Data migration quality issues delay go-live | Technical | Ahmed Al-Rashid | 2 | 2 | 4 | Reduce | Run parallel migration dry-runs; define acceptance criteria | Extend UAT window by two weeks | Open | 2026-04-10 | 2026-05-15 | Dry-run #1 planned for May 3
R-004 | Budget overrun due to unplanned regulatory requirement | Financial | Lena Bergström | 1 | 3 | 3 | Transfer | Engage legal counsel; include contingency in budget plan | Request emergency budget approval from Finance Director | On Hold | 2026-04-12 | 2026-05-01 | Awaiting legal opinion
R-005 | Loss of key SME during implementation phase | HR/People | Jan de Vries | 2 | 2 | 4 | Reduce | Cross-train backup resource; document knowledge base | Engage interim consultant from preferred supplier list | Open | 2026-04-15 | 2026-05-15 | Knowledge transfer plan drafted
PMO Mastery ¦ RAID Log ¦ pmomastery.com

## Assumptions
RAID Log – Assumptions
Assumption ID | Assumption Description | Category | Owner | Rationale / Basis | Impact if Wrong | Validation Actions | Status | Date Raised | Review Date | Notes
A-001 | Business users will be available for UAT during weeks 30–32 | Operational | Sophie Müller | Agreed in project charter; sign-off from Line Managers received | UAT delayed; go-live pushed back 4+ weeks | Confirm resource availability with Line Managers by 1 May | Confirmed | 2026-04-01 | 2026-05-01 | Written confirmation received 3 Apr
A-002 | Existing ERP system can support the new integration via standard API | Technical | Ahmed Al-Rashid | Initial vendor assessment indicates standard REST API available | Custom development required; +€40k budget impact | Complete technical spike by 15 May; confirm API capabilities | Unconfirmed | 2026-04-05 | 2026-05-15 | Spike in progress
A-003 | Regulatory framework remains unchanged through go-live date | Legal/Compliance | Lena Bergström | No announced changes; legal team monitoring legislative pipeline | Redesign of compliance module required; 6-week delay | Monthly check with legal counsel; subscribe to regulatory alerts | Confirmed | 2026-04-08 | 2026-05-01 | Next legal review 1 May
A-004 | Current team headcount is sufficient to cover implementation and BAU | HR/People | Jan de Vries | Resource plan signed off at project kick-off | Quality issues; burnout risk; need to hire interim resource | Track utilisation weekly; flag if >85% sustained over 2 weeks | Unconfirmed | 2026-04-10 | 2026-04-30 | First utilisation report due 30 Apr
A-005 | Training can be delivered entirely online without face-to-face sessions | Operational | Sophie Müller | Post-COVID preference; LMS platform already licensed | Lower adoption; need in-person sessions (+€8k travel cost) | Conduct readiness survey with end-user group in May | Unconfirmed | 2026-04-15 | 2026-05-15 | Survey draft under review
PMO Mastery ¦ RAID Log ¦ pmomastery.com

## Issues
RAID Log – Issues
Issue ID | Issue Description | Category | Issue Owner | Priority | Impact on Project | Resolution Actions | Status | Date Raised | Target Resolution | Date Resolved | Notes
I-001 | Development environment unavailable for 3 days due to server outage | Technical | Ahmed Al-Rashid | High | 3-day delay to sprint delivery; compensating actions required | IT team resolved outage 28 Apr; sprint replanning completed | Resolved | 2026-04-25 | 2026-04-28 | 2026-04-28 | Root cause: storage failure – patched and monitored
I-002 | Key data from legacy system cannot be exported in required format | Technical | Ahmed Al-Rashid | Critical | Migration blocked; go-live at risk without workaround | Engage vendor for bespoke export tool; manual transformation as interim | In Progress | 2026-04-20 | 2026-05-10 |  | Vendor response expected by 5 May
I-003 | Stakeholder sign-off on requirements delayed by 2 weeks | Operational | Sophie Müller | High | Design phase delayed; downstream tasks on hold | Escalated to Sponsor; interim approval granted for high-priority items | In Progress | 2026-04-15 | 2026-05-02 |  | Full sign-off meeting rescheduled to 2 May
I-004 | Training material translation into French incomplete | HR/People | Jan de Vries | Medium | French-speaking users cannot begin self-paced training on schedule | Engage external translation bureau; deliverable by 20 May | Open | 2026-04-22 | 2026-05-20 |  | PO raised; translation bureau confirmed
I-005 | Finance sign-off required for change request above €10k threshold | Financial | Lena Bergström | Medium | Change request on hold; 1-week delay to procurement | Submit formal CR to Finance Director; expedite review | On Hold | 2026-04-18 | 2026-05-05 |  | CR submitted 19 Apr; Finance review pending
PMO Mastery ¦ RAID Log ¦ pmomastery.com

## Dependencies
RAID Log – Dependencies
Dep. ID | Dependency Description | Type | Dependency Owner | Related Project / Team | Due Date | Status | Impact if Delayed | Mitigation | Notes
D-001 | Completion of infrastructure upgrade by IT Operations before go-live | Internal | Ahmed Al-Rashid | IT Operations | 2026-05-31 | Active | Go-live date cannot be met; project delay of minimum 4 weeks | Weekly sync with IT Ops; escalation path agreed with CTO | Infrastructure team on track as of 28 Apr
D-002 | Supplier API documentation and sandbox access from ERP vendor | External | Ahmed Al-Rashid | Vendor: CoreSystems BV | 2026-05-10 | At Risk | Integration development blocked; 3-week delay to sprint 4 | Account manager engaged; daily follow-up; contractual SLA referenced | Escalated to vendor account manager 29 Apr
D-003 | Approval of data governance policy by Information Security | Internal | Lena Bergström | Information Security | 2026-05-15 | Active | Data migration cannot commence; GDPR compliance gap | Draft policy shared for review; review meeting booked 6 May | Policy review in progress
D-004 | Completion of parallel HR system migration by People & Culture | Internal | Sophie Müller | People & Culture | 2026-06-01 | Active | User provisioning and access management delayed | Monthly cross-project sync; shared dependency log maintained | P&C migration on schedule; next milestone 15 May
D-005 | Regulatory pre-approval from national authority before go-live | External | Lena Bergström | Regulatory Authority NL | 2026-05-20 | At Risk | Go-live legally prohibited until approval received | Application submitted 1 Apr; legal counsel monitoring; contingency date built in | Authority acknowledgement received; decision expected 15 May
PMO Mastery ¦ RAID Log ¦ pmomastery.com