## Instructions
Risk Log Template – Instructions
How to use this risk log
Purpose
This template helps project and programme teams systematically identify, assess, and manage risks throughout the project lifecycle. It provides a structured register for tracking all risks in one place, ensuring nothing falls through the cracks.
Column Guide
Risk ID | Auto-reference number (e.g. R-001). Use sequential numbering. Never reuse an ID once assigned.
Date Identified | The date the risk was first logged. Use DD-MM-YYYY format.
Category | Select from the dropdown: Strategic, Operational, Financial, Technical, Legal/Compliance, HR/People, External, Other.
Risk Description | Describe the risk clearly in one or two sentences. State what could go wrong and in which context.
Cause | What triggers this risk? Briefly describe the root cause or source.
Impact Description | Describe what would happen to the project if this risk materialises. Focus on scope, time, cost, or quality.
Probability (1-5) | Rate the likelihood: 1 = Very Low ¦ 2 = Low ¦ 3 = Medium ¦ 4 = High ¦ 5 = Very High
Impact (1-5) | Rate the consequence: 1 = Negligible ¦ 2 = Minor ¦ 3 = Moderate ¦ 4 = Major ¦ 5 = Critical
Risk Score | Calculated automatically: Probability × Impact. Range 1–25. Used to prioritise risks.
Risk Level | Derived automatically from score: Low (1–4) ¦ Medium (5–9) ¦ High (10–14) ¦ Critical (15–25).
Risk Owner | The person responsible for monitoring and managing this risk. One owner per risk.
Response Strategy | Select from dropdown: Avoid, Reduce, Transfer, Accept, or Escalate.
Response Actions | Describe specific actions planned or taken to address the risk.
Target Date | The deadline for completing response actions or reviewing the risk.
Status | Select: Open, In Progress, Resolved, or Closed. Update at every review cycle.
Last Reviewed | Date of the most recent review or update to this risk entry.
Notes / Escalation | Any additional context, escalation notes, decisions made, or links to related documents.
Risk Scoring Matrix (Probability × Impact)
| Impact 1 Negligible | Impact 2 Minor | Impact 3 Moderate | Impact 4 Major | Impact 5 Critical
Prob 1 Very Low | 1 | 2 | 3 | 4 | 5
Prob 2 Low | 2 | 4 | 6 | 8 | 10
Prob 3 Medium | 3 | 6 | 9 | 12 | 15
Prob 4 High | 4 | 8 | 12 | 16 | 20
Prob 5 Very High | 5 | 10 | 15 | 20 | 25
Score Legend
1–4 | Low
5–9 | Medium
10–14 | High
15–25 | Critical
Best Practices
Review cadence | Review the risk log at every project status meeting — at minimum weekly for active projects.
Ownership | Every risk must have a named owner. Do not assign risks to a team — one person is accountable.
Active management | A risk log is not a 'set and forget' document. Update Status and Last Reviewed at every review.
Escalation | Escalate Critical risks (score 15–25) to the project sponsor or steering committee immediately.
Closed risks | Do not delete resolved risks. Set Status to 'Closed' to preserve the audit trail.
Opportunities | Adapt this log to track positive risks (opportunities) using a separate tab or indicator column.
PMO Mastery ¦ Risk Log Template ¦ pmomastery.com

## Risk Log
Risk Log
Risk ID | Date Identified | Category | Risk Description | Cause | Impact Description | Probability (1–5) | Impact (1–5) | Risk Score | Risk Level | Risk Owner | Response Strategy | Response Actions | Target Date | Status | Last Reviewed | Notes / Escalation
R-001 | 01-04-2026 | Technical | The integration between the new ERP system and legacy HR platform may fail, causing data synchronisation errors. | Incompatible API versions between systems. | Payroll data will not transfer correctly, delaying go-live by 2–4 weeks and affecting 300 employees. | 3 | 4 | 12 | High | Fatima Al-Hassan | Reduce | Engage integration vendor to perform compatibility testing by 15-04-2026. Establish fallback manual process. | 15-04-2026 | In Progress | 20-04-2026 | Escalated to IT steering committee on 18-04.
R-002 | 05-04-2026 | Financial | Project budget may be insufficient if third-party consultancy invoices exceed the capped amount in the contract. | Contract cap was set 18 months ago; scope has expanded. | Cost overrun of €30k–€60k, requiring budget re-approval from the board. | 2 | 3 | 6 | Medium | Jorn Bakker | Transfer | Review contract with legal. Negotiate revised cap or fixed-price addendum. Confirm by 30-04-2026. | 30-04-2026 | Open | 20-04-2026 | Contract review meeting scheduled 28-04.
R-003 | 08-04-2026 | HR/People | Two key team members may leave the project before completion due to competing internal priorities. | Resource allocation not formally confirmed by line managers. | Loss of critical knowledge and delay of 3–6 weeks while onboarding replacements. | 4 | 3 | 12 | High | Priya Sharma | Reduce | Formalise resource allocation with written confirmation from department heads. Arrange knowledge transfer sessions. | 10-04-2026 | Open | 20-04-2026
R-004 | 10-04-2026 | External | New GDPR enforcement guidance expected in Q2 2026 may require rework of the data processing module. | Regulatory change driven by EU supervisory authority. | Rework could cost €15k–€25k and add 3 weeks to the schedule. | 2 | 4 | 8 | Medium | Lena Müller | Accept | Monitor regulatory publications weekly. Assign legal counsel to track guidance. No action until guidance is confirmed. | 01-06-2026 | Open | 20-04-2026 | Low probability but high impact — accepted for now.
R-005 | 12-04-2026 | Operational | Stakeholder sign-off may be delayed if key sponsor is unavailable during the approval window in May. | Sponsor travelling internationally for 3 weeks in May. | Delay in phase gate approval, pushing the project end date back by 2–3 weeks. | 3 | 3 | 9 | Medium | Marco de Wit | Avoid | Pre-schedule approval session for 29-04-2026. Prepare all deliverables 2 weeks in advance. Arrange delegate approval authority. | 29-04-2026 | Open | 20-04-2026
R-006 | [7 empty] | 0 | Low
R-007 | [7 empty] | 0 | Low
R-008 | [7 empty] | 0 | Low
R-009 | [7 empty] | 0 | Low
R-010 | [7 empty] | 0 | Low
R-011 | [7 empty] | 0 | Low
R-012 | [7 empty] | 0 | Low
R-013 | [7 empty] | 0 | Low
R-014 | [7 empty] | 0 | Low
R-015 | [7 empty] | 0 | Low
R-016 | [7 empty] | 0 | Low
R-017 | [7 empty] | 0 | Low
R-018 | [7 empty] | 0 | Low
R-019 | [7 empty] | 0 | Low
R-020 | [7 empty] | 0 | Low
R-021 | [7 empty] | 0 | Low
R-022 | [7 empty] | 0 | Low
R-023 | [7 empty] | 0 | Low
R-024 | [7 empty] | 0 | Low
R-025 | [7 empty] | 0 | Low
PMO Mastery ¦ Risk Log ¦ pmomastery.com